COLLEGE OF SOCIAL SCIENCES AND HUMANITIES

CENTER OF EXCELLENCE IN HUMAN AND SOCIAL DEVELOPMENT

DISTINGUISHED CHAIR VALUES AND EDUCATION

Responsible:

Alberto Garate Rivera.

February 2011

This distinguished chair framed in the Center of Human and Social Development will start on May 2, 2011, and will be inaugurated by the retired professor from the University of Murcia, Dr. Pedro Ortega Ruiz.

The distinguished chair considers two periods of face-to face work in 2011:

a) From May 2 - 27. Dr. Pedro Ortega R.

b) From November 2-30. Dr. Ramon Minguez Vallejo.

The distinguished Chair of Values and Education is made out of four sub-programs:

- Educational Research Intervention named: Family and values in the Mexicali society. The study will be conducted by Ortega & Minguez (University of Murcia) and by Professor Luis E. Linares Borboa and Dr. Alberto Garate Rivera (CETYS University).  Students from the bachelor’s degrees that are enrolled in the Research Methodology course will join in, as well as students of the master's degree in Education. The study will be completed on May 2012.

2.   Doctoral Theses. A Methodological Counseling seminar will take place throughout the weeks of May and November for students of the Doctoral degree in Education and Values, and whose level of advancement may predict that they will finish their thesis this year.

3.   Master's Degree in Education. A seminar on family and values will be scheduled for the students of the Master's Degree in Education in which the students of the bachelor’s degree in Education Sciences will be able to participate. 20 hours of on-site work will be considered.

4.   Conferences. Both Doctors Ortega and Minguez will offer conferences to the CETYS and the Baja Californian community in the cities of Ensenada, Tijuana, and Mexicali. We are considering at least five of these activities in each one of the periods.

With regard to the research work

- Develop a research work of a quantitative nature during one year on the values of the Mexicali family.

b)   The work will be based on an instrument editable and adaptable that has been applied in Murcia that would recover information in two aspects: what values does the Mexicali family say it possesses? How are these values expressed in the forms of life-praxis?

c)   The contribution of the study is given precisely by the dimension of its praxis. The research team will ensure that the instrument goes from the identification to the forms of living.

Although we identify strata in the implementation of the instrument, it will be discussed in May 2011; right now we propose that a representative sample will be applied by strata.

e)   The research group of Mexicali shall write a chapter on the Mexicali family from the historical and cultural perspective. It will be ready for May 2011.

f)   The research group of Murcia shall write a conceptual framework on family and values, and will add the data collection instrument (survey) for May 2011.

g)   The second phase of research will be qualitative in nature - discussion groups - and will be defined according to the results of the quantitative study. This part is essential in order to develop the program of pedagogical intervention. This will be in the spring of 2012.

h)   The empirical stage of study (I (applying the survey) will be carried out in the summer and autumn of this year.

i)    From December 2011 to March 2012 the data analysis and interpretation will take place. The report will be prepared for May 2012.

With regard to the Doctoral theses

•    Students that have an adequate progress are selected, so they can have the possibility of taking the professional exam this year.

•     The Spaniards will work on the methodological part during eight sessions of three to four hours each.

•      Ideally we would benefit from the presence of Minguez for processing the first degree exams (November 2011).

With regard to the seminars, the work aspect would be values and education. We propose to the coordination of the Master's degree in Education the possibility of working the face-to-face 20-hour seminar in two days during two weeks.

Respecto a los seminarios

La vertiente de trabajo sería valores y educación.

Plantearnos con la coordinación de la Maestría en Educacion la posibilidad de trabajar el seminario de 20 horas presenciales en dos días durante dos semanas.

COLLEGE OF SOCIAL SCIENCES AND HUMANITIES

CENTER OF EXCELLENCE IN HUMAN AND SOCIAL DEVELOPMENT

CENTER OF HUMANISM RESEARCH AND EDUCATION

DISTINGUISHED CHAIR VALUES AND EDUCATION

PROGRAM OF ACTIVITIES

WEEK 1

Tuesday, May 3

Arrival of Dr. Pedro Ortega Ruiz. Wednesday May 4 Educational research intervention and Family Values in the Mexicali society.

17-19 Hours Conference Distinguished Chair Values and Education. Addressed to the general public. CETYS Auditorium Mexicali Campus. Thursday, May 5

17:00-20:00 hrs Methodological Counseling seminar for students of the Doctoral degree in Education (group session).

Friday, May 6,

17:00-20:00 hrs Individual Counseling seminar for students of the Doctoral degree in Education.

Saturday May 7,

09:00-11:00 hrs Informal chat with faculty and students of the College of Social Sciences and Hum. (Gallego Conference Room. 30 Guests).

WEEK 2

Monday, May 9

Educational research intervention and Family Values in the Mexicali society. Field work.

Organizing working meeting with the research team…it includes Liliana, Carlos Luis Linares, and Teresita.

Tuesday, May 10 Educational research intervention and Family Values in the Mexicali society.

17:00-21:00 hrs Family and values seminar for the students of the Master's degree in Education. Training Room of the Library.

Wednesday May 11

17:00-21:00 hrs Family and values seminar for the students of the Master's degree in Education. Training Room of the Library.

Thursday, may 12

17:00-20:00 hrs Methodological Counseling seminar for students of the Doctoral degree in Education. (Individual Session)

Friday, May 13

7 a.m. Departure to Tijuana. Talk with undergraduate students in the morning from 11 to 13 hours at the CETYS Graduate area. Chat with members of APEC in the afternoon. Country Club, 19 hours.

Saturday May 14

09:00-11:00 hrs Conference Distinguished Chair Values and Education. Aimed at the students of the Master's degree in Education. Auditorium of the Tijuana Campus.

WEEK 3

Monday, May 16 Educational research intervention and family values in the Mexicali society.

Tuesday, May 17 Educational research intervention and Family Values in the Mexicali society.

17:00-21:00 hrs Seminar on Family and Values for students of the Master's degree in Education. Training Room of the Library

Wednesday May 18,

17:00-21:00 hrs Seminar on family and values for students of the Master's Degree in Education. Training Room of the Library.

Thursday, may 19

17:00-20:00 hrs Methodological Counseling seminar for students of the Doctoral degree in Education.

Friday, May 20

7 a.m. Departure to Ensenada. Conversation with students and guests in the morning from 11 to 13 hours at the CETYS Graduate area.

Saturday May 21

09:00-11:00 hrs Conference Distinguished Chair Values and Education. Aimed at the students of the Master's degree in Education. Library of the Ensenada Campus.

WEEK 4

Monday, May 23 Educational research intervention and Family Values in the Mexicali society.

Tuesday, May 24 Educational research intervention and Family Values in the Mexicali society.

Wednesday May 25 Educational research intervention and Family Values in the Mexicali society.

Thursday, may 26

17:00-20:00 hrs Methodological Counseling seminar students of the Doctoral degree in Education.

Friday, may 27

17:00-20:00 hrs Methodological Counseling seminar students of the Doctoral degree in Education.

Evaluation of the Distinguished Chair